## Roadmap
ID | Workstream | Capability | Target | Availability | Team | Status | Start | End | Relevant
WK-01 | Foundation | Booking intake | Shared booking form | Available | Delivery | In progress | 2026-11-02 | 2026-11-06 | Yes
WK-02 | Operations | Equipment register | Reviewed inventory | Gap | Operations | Not started | 2026-11-09 | 2026-11-13 | Yes
WK-03 | Transition | Operator handover | Documented runbook | Unknown |  | Not started |  |  | Yes
WK-04 | Future | Fee collection | Future decision | Unknown |  | Not started |  |  | No

## RACI
Roadmap ID | Area | Delivery | Operations | Sponsor | Notes
WK-01 | Booking design | RA | C | I | Review with volunteers
WK-02 | Register ownership | R | C | I | Accountability is intentionally missing for review

## Dependencies
Roadmap ID | Dependency | Owner | Status
WK-02 | Confirm equipment naming convention | Operations coordinator | Open

## Scorecard
Criterion | Weight | Score | Notes
Usability | 60 | 4 | Synthetic workshop assessment
Maintainability | 40 | 3 | Human score; not a forecast